## Slide 1
Semester 2 Planning Activity Timeline
Stage
Month | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  |  | December |  |  | 
Week Commencing | 9 | 16 | 26 | 30 | 6 | 13 | 20 | 27 | 5 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27
Key Milestones & Decision Points |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Teaching Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Timetabling & Registration and Enrolment Support Teams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comms & Engagement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
August Exams
1
Commence Data Gathering
3
Conclude Data Gathering
5
Publish Updated Timetable
6
Review changes/ allocations and make adjustments
CTT & MSDI build test system and complete test scenarios
CTT produce data gathering tools
Confirm governance arrangements
Determine complexity and impact
Schools complete initial data gathering
Determine process, protocols and priorities for system/data updates
Reporting on progress
Schools complete detailed data gathering and make changes to CMIS / raise change requests
SMG decision point
1
Develop timeline and staff comms
Develop resource plan
Plan student comms
Dec Exams
2
Approve revised Planning Principles
4
Close CMIS & create copy of data
CTT Apply changes to CMIS & allocate rooms
Enrolment Support (as required)
CMIS Closed
Staff Comms
CTT manage changes & report on unresolved issues / unroomed events
Student comms
Publish Guidance on managing adjustments
Schools to create additional complementary learning-related events
Explore options to publish complementary learning related events
Schools review changes / allocations and make adjustments